## Sheet1
BRD ID | Business Requirement | Use Case ID | UAT ID | User Story ID | Status | Notes
BR-01 | The system must allow fresh graduates to create an account and log in securely. | UC-01 | UAT-001 | — | In Progress | Login/Register (Job Seeker)
BR-02 | The system must allow job seekers to create and update a professional profile. | UC-02 | UAT-002 | — | Not Started | Profile creation flow
BR-03 | The system must provide personalized job recommendations based on user profiles. | UC-03 | UAT-003 | — | Not Started | AI-based recommendation logic
BR-04 | Job seekers must be able to search and apply for jobs using relevant filters. | UC-04 | UAT-004 | — | Not Started | Job search & apply
BR-05 | The system must allow employers to register and access their own dashboard. | UC-05 | UAT-005 | — | Not Started | Employer Registration/Login
BR-06 | Employers must be able to post new job openings with full job descriptions. | UC-06 | UAT-006 | — | Not Started | Post Job
BR-07 | Employers should be able to view applicants for each job posting. | UC-06 | UAT-007 | — | Not Started | View Applicants & Manage
BR-08 | Employers must receive a list of AI-suggested candidates based on job requirements. | — | — | — | Not Started | AI matching logic (future)
BR-09 | Job seekers must be able to track the status of their job applications. | — | — | — | Not Started | Candidate dashboard functionality
BR-10 | The platform must provide a user-friendly and mobile-responsive interface. | — | — | — | Not Started | UI/UX focused requirement
BR-11 | The system must support basic admin controls for platform oversight. | — | — | — | Out of Scope | Out of current scope
BR-12 | The system should allow users to submit feedback or contact support. | — | — | — | Not Started | Future enhancement